PRODUCT IMPLEMENTATION PLAN

erFam

Contract-first, evidence-gated build plan for Android, administration, cloud control, media, and locked carrier integration

| Field | Value |
| --- | --- |
| Version | 0.1 |
| Status | Build-start candidate — alpha review required |
| Prepared | 24 July 2026 |
| Governing requirements | erFam PRD v0.3 |
| Governing design | erFam Product Design v0.2 |
| Build boundary | B1–B6 only; no live carrier activation |
| Primary architecture | Android + Next.js admin + Kotlin/Ktor + PostgreSQL + Asterisk/TURN |
| Carrier adapter | Simulator and real driver delivered; real driver fake-transport tested and activation-locked |

Planning promise The plan does not promise that complex software has zero uncertainty. It makes uncertainty explicit, bounds it with spikes and contracts, fails closed, and prohibits silent semantic drift. No phase advances on confidence alone; it advances on named evidence.

# 1. Executive build decision

Proceed to implementation only after alpha approval Use a contract-first modular monolith and vertical-slice delivery. Establish semantic primitives, activation locks, API/event contracts, repository controls, and simulator media before feature teams fan out. Build the real adapter in the same program, but validate it only with fake/vendor-lab transport and keep every live route independently locked.

| Control | Decision | Consequence |
| --- | --- | --- |
| Scope | Build-track gates B1–B6. | Written carrier approval and live hardware tests remain L0–L4. |
| Delivery unit | Small vertical increments behind typed contracts and feature controls. | Every merge leaves the main branch deployable. |
| Authority | Server/PostgreSQL state; PBX/local timers provide bounded safety. | Clients, cache, and lease expiry cannot invent truth. |
| Parallelism | Only after contract and ownership freeze; disjoint packages. | Shared schema/state/security edits remain serialized. |
| Carrier driver | Production-intent real driver plus fake/vendor transport. | Implementation complete is never labelled hardware-verified or authorized. |
| Quality | Evidence matrix, negative proof, fault injection, and alpha veto. | No package is complete because code merely compiles. |
| Model policy | Sol 5.6 alpha for critical review; Terra for bounded implementation. | Mechanical work consumes fewer credits without lowering review standards. |

## 1.1 Definition of the B6 outcome

- Twelve configurable members can enroll one cryptographic Android device, request/receive minutes, and place simulated calls through the full production-shaped stack.

- The admin can operate members, grants, calls, privacy reveal, configuration, incidents, and physical tasks through the responsive web application.

- Asterisk/WebRTC/TURN, call state, caps, reconnect, queue, ledgers, retention, audit, and reconciliation pass automated and fault-injection evidence.

- SimulatorAdapter and RealGatewayAdapter pass one conformance suite; the real adapter is deployable in locked/dry-run form only.

- Persistent Demo — no real phone call is placed labeling is present, and negative tests prove no non-authorized environment can emit a carrier command.

- Runbooks, monitoring, backup/restore, incident controls, build provenance, and evidence pack are complete.

## 1.2 Explicitly outside this plan

- Carrier/regulatory approval, exact du live-route authorization, SIM activation, or consumer-plan assumption.

- Authorized exact-hardware VoLTE interoperability and the 100-call live acceptance program.

- iOS member application, browser calling, multiple simultaneous real lines, payments, AI allocation, or public distribution.

- Server-accessible recording or any recording activation before approved recipient-consent policy.

# 2. Sequencing and dependency strategy

Figure 1. Work fans out only after contracts and locked invariants are fixed.

## 2.1 Contract-first order

Real-adapter integration surface is decided The real adapter uses a standards-based SIP/PJSIP line driver through Asterisk and a separate GatewayTelemetryPlugin. The baseline plugin derives health from SIP registration/OPTIONS and correlated PBX events/CDR; a vendor-specific plugin may add richer management evidence. This makes the B1–B6 target concrete without claiming exact hardware interoperability before L1.

- Freeze shared vocabulary, integer units, authoritative states, E.164 policy, role permissions, configuration precedence, error taxonomy, and activation-generation semantics.

- Publish machine-readable OpenAPI, AsyncAPI, database migration conventions, adapter interface, protobuf/JSON schemas, and test fixtures.

- Create the monorepo, CI policies, environments, secrets placeholders, observability envelope, and locked network topology.

- Deliver one thin vertical simulator slice: enroll → grant → call intent → WebRTC/PBX → simulated answer → ledger/history.

- Expand domain capabilities and Android/admin flows behind the stable contracts.

- Implement the real adapter and local edge against fake/vendor transport; prove all live paths locked.

- Run integrated reliability, security, privacy, accessibility, retention, backup/restore, and B6 demonstration evidence.

## 2.2 Work that must not run in parallel

| Serialized decision | Why | Unlocks |
| --- | --- | --- |
| Call state/event reducer | Two implementations would create incompatible truth and race behavior. | Backend, Android, admin, PBX bridge, adapter tests. |
| Ledger entry taxonomy | Parallel edits risk double debit/grant and irreconcilable reporting. | Allocation, call admission, history, reconciliation. |
| CarrierAdapter contract | Driver-specific branching defeats parity and locked negative proof. | Simulator, real driver, orchestrator, edge. |
| Identity/device lifecycle | Migration/revocation races are security boundaries. | Android auth, admin recovery, API sessions. |
| Configuration schema/precedence | Ordinary config must never weaken immutable constraints. | All services and admin settings. |
| Privacy/logging schema | Telemetry emitted before classification can permanently leak PII. | Every runtime and test harness. |

# 3. Repository, contracts, and integration governance

## 3.1 Monorepo layout

| Path | Owner | Contents / boundary |
| --- | --- | --- |
| apps/android | Android lead | Compose UI, device enrollment, WebRTC/audio, local data, FCM, accessibility. |
| apps/admin | Admin lead | Next.js admin UX, typed client, permissions, step-up, operational views. |
| services/control | Backend lead | Ktor API/worker profiles and domain modules. |
| services/media-control | Media lead | ARI/PJSIP bridge, normalized PBX events, simulator integration. |
| services/home-edge | Adapter lead | Real adapter process, fake/vendor transport, local watchdog, tunnel agent. |
| contracts | Integration lead | OpenAPI, AsyncAPI, adapter schemas, fixtures, semantic catalogue. |
| infra | Platform lead | Compose, Terraform, deployment, policies, secrets references, observability. |
| tests | QA lead | Contract, E2E, property, SIP/WebRTC, fault, security, retention, evidence tooling. |
| docs/adr + runbooks | Integration/contract lead; alpha reviews | Decisions, threats, operations, evidence and gate records. |

## 3.2 Contract change protocol

- Author opens a Contract Change Record with affected invariant, compatibility class, migration, tests, rollback, and owners.

- Integration lead checks schema compatibility and regenerates typed clients/fixtures in one change.

- Security/privacy reviewer checks route, identity, activation, logging, retention, and recording boundaries.

- Android/admin/media owners approve consumer impact; alpha approves semantic or security-critical changes.

- Change merges before dependent work rebases; dual-schema compatibility exists for rolling deployments when required.

- Old schema is removed only after deployed-consumer evidence and rollback window close.

## 3.3 Merge contract

- Every work package uses immutable ID ERF-<catalogue ID> and declares allowed paths, preconditions, outputs, acceptance tests, telemetry, evidence, reasoning/model class, and rollback before an agent begins.

- Agents do not edit another package's owned paths or a shared contract without an accepted change record.

- Each merge is small, reviewable, signed/attributable, and green on required checks; incomplete features stay disabled.

- Generated API clients, migrations, fixtures, and documentation are committed with their source contract.

- No direct database access crosses module ownership; integration occurs through typed application commands/events/read models.

# 4. Work-package catalogue

Effort is relative: S ≈ 1–2, M ≈ 3–5, L ≈ 6–10, XL ≈ 10–15 focused engineering days before review. These are planning weights, not schedule promises.

## 4.1 Foundation and contracts

| ID | Package | Size | Depends | Primary output | Completion evidence |
| --- | --- | --- | --- | --- | --- |
| FND-01 | Semantic catalogue + ADRs | M | PRD/design | States, units, invariants, errors, role matrix, ADR-001…015 | Alpha sign-off; semantic property checklist |
| FND-02 | Monorepo and build system | M | FND-01 | Gradle/Node roots, formatting, dependency locks, ownership | Clean bootstrap; reproducible build |
| FND-03 | OpenAPI/AsyncAPI/schema pipeline | L | FND-01 | Versioned contracts, generated clients, compatibility check | Golden fixtures; breaking-change detector |
| FND-04 | CI quality and supply chain | L | FND-02 | Checks, SBOM, secret/SAST/dependency/license scans, signing | Protected main; provenance artifact |
| FND-05 | Environments and locked network | L | FND-02 | Compose, staging IaC, no carrier route, secret placeholders | Network negative proof |
| FND-06 | Telemetry/privacy envelope | M | FND-01 | Correlation, redaction, metric taxonomy, alert skeleton | Canary PII log tests |

## 4.2 Backend and data authority

| ID | Package | Size | Depends | Primary output | Completion evidence |
| --- | --- | --- | --- | --- | --- |
| BE-01 | Domain primitives | M | FND-01/03 | Integer seconds/fils, UTC/monotonic time, E.164 parser, typed IDs | Property tests; Unicode/emergency corpus |
| BE-02 | Identity/device/roles | XL | BE-01 | Invite, OTP abstraction, Keystore proof, sessions, migration/recovery, RBAC | Replay/revocation/race tests |
| BE-03 | Configuration authority | L | BE-01 | Typed versions, precedence, diff, publish, rollback, snapshots | Invalid/missing config fails closed |
| BE-04 | Audit/privacy/crypto | XL | BE-01/03 | Envelope encryption, masking, reveal, audit, key rotation hooks | No plaintext/log; reasoned reveal evidence |
| BE-05 | Minutes/fairness/ledgers | XL | BE-01/03 | Requests, deterministic recommendation, grants, entitlement ledger | Determinism, no underflow, compensation |
| BE-06 | Call state and admission | XL | BE-01/03/05 | State reducer, cap, reservation, authoritative answer, reconnect | Model/property and boundary tests |
| BE-07 | Fenced lines/outbox/inbox | L | BE-06 | Atomic lease, epochs, commands, dedupe, jobs, reconciliation hold | Crash/concurrency/late-event tests |
| BE-08 | Queue/claims/notifications | L | BE-05/07 | Waitlist, 60-second claim, FCM wake, preferences | No auto-dial/reservation; expiry tests |
| BE-09 | History/retention/reconciliation | XL | BE-04/05/06 | P4M purge, carrier-evidence abstraction, three-ledger cases | Month-end/restore/purge/compensation |

## 4.3 Media, simulator, and locked real adapter

| ID | Package | Size | Depends | Primary output | Completion evidence |
| --- | --- | --- | --- | --- | --- |
| TEL-01 | Android–Asterisk spike | L | FND-05 | WebRTC WSS/DTLS-SRTP, Opus, audio routing, reconnect evidence | Target-device trace and decision |
| TEL-02 | Asterisk/TURN baseline | L | TEL-01 | Pinned image, PJSIP/ARI, trusted TLS, TURN, no public admin | SIPp/WebRTC suite; config scan |
| TEL-03 | PBX event bridge | XL | BE-06/TEL-02 | Normalized answer/alert/end, cap/watchdog, correlation | Early-media/late/duplicate/fault tests |
| TEL-04 | CarrierAdapter SDK + SIP line port | L | FND-03/BE-07,TEL-02 | Versioned port, standard Asterisk/PJSIP call boundary, capability flags, UNKNOWN/UNSUPPORTED health | Shared conformance suite |
| TEL-05 | SimulatorAdapter | L | TEL-04 | Deterministic scenarios, fake clock, scripted faults/evidence | All contract cases; reproducible seeds |
| TEL-06 | RealGatewayAdapter + telemetry plugin | XL | TEL-04 | Production SIP/PJSIP driver, baseline SIP/ARI/CDR plugin, optional vendor plugin port, fake/vendor transport | Same conformance; zero carrier command |
| TEL-07 | Activation and kill enforcement | XL | BE-03/07,TEL-02/06 | Generation manifest, PBX route lock, adapter lock, four kill modes | Stale/missing/compromised-layer negative proof |
| TEL-08 | Home-edge/watchdog/tunnel | L | FND-05,TEL-06/07 | Outbound tunnel agent, local expiry/watchdog, safe status and config | Cloud-loss/orphan-leg simulation |

## 4.4 Android member application

| ID | Package | Size | Depends | Primary output | Completion evidence |
| --- | --- | --- | --- | --- | --- |
| AND-01 | App shell/design system | M | FND-02 | Compose navigation, tokens, demo banner, localization/a11y harness | Screenshot/a11y/pseudo-locale |
| AND-02 | Enrollment/device security | XL | BE-02,FND-03 | Invite/OTP, Keystore proof, sessions, migration/recovery | One-device/reinstall/revoke matrix |
| AND-03 | Contacts/dialer/preflight | L | BE-01/06 | App contacts, optional picker, E.164 UX, emergency exclusion | Permission denial + route corpus |
| AND-04 | Call state and controls | XL | TEL-03/05 | Truthful states, controls, DTMF, cap/reconnect/finalizing | No false Connected; process/network tests |
| AND-05 | Media/audio foreground service | XL | TEL-01/02 | WebRTC module, foreground call, routes, lock screen, battery | 12-device and network matrix |
| AND-06 | Minutes/queue/history | L | BE-05/08/09 | Requests, grants, claims, own history, reconciliation | Offline/stale/push failure UX |
| AND-07 | Local recording gated skeleton | M | AND-04 | No baseline control; encrypted local module and consent hooks disabled | No server path/backup; feature-off proof |
| AND-08 | Hardening and release | L | AND-01…07 | TalkBack, Tigrinya samples, RTL isolation, performance, obfuscation | Quality/device/release evidence |

## 4.5 Administration web

| ID | Package | Size | Depends | Primary output | Completion evidence |
| --- | --- | --- | --- | --- | --- |
| WEB-01 | Shell/auth/permission UI | L | BE-02,FND-03 | Responsive shell, MFA/step-up, scope guards, error states | Role/route/CSRF/CSP tests |
| WEB-02 | Requests and allocation | L | BE-05 | Queue, recommendation explanation, approve/edit/reject/override | Deterministic inputs; reason/audit |
| WEB-03 | Members/devices/roles | L | BE-02 | Invite, suspend, recovery, migration, delegated permissions | Consequence-specific confirmations |
| WEB-04 | Calls/privacy/reconciliation | L | BE-04/06/09 | Masked history, reveal, force end, cases, exports | Step-up/reason/no recording access |
| WEB-05 | Service/gateway/incidents | L | TEL-05…08 | Separate implementation/test/lock/health status, four kill controls | No Enable; truthful locked/outage states |
| WEB-06 | Configuration/audit/physical tasks | XL | BE-03/04 | Draft/diff/publish/rollback, audit, incident tasks | Locked fields immutable; drift/rollback |

## 4.6 Quality, security, operations, and evidence

| ID | Package | Size | Depends | Primary output | Completion evidence |
| --- | --- | --- | --- | --- | --- |
| QAO-01 | Test orchestration | L | FND-02/03 | Fixtures, fake clock, containers, emulator/SIP drivers, evidence index | One command per suite; deterministic rerun |
| QAO-02 | Threat model/security suite | XL | FND-01 onward | Toll fraud, injection, replay, admin, gateway, logging, rooted device | All critical controls tested; alpha review |
| QAO-03 | Reliability/performance/faults | XL | Vertical slice | Load, deploy/restart, tunnel/DB/KMS/PBX loss, alert/kill failure | SLO and no-orphan/no-duplicate evidence |
| QAO-04 | Privacy/retention/backup | L | BE-04/09 | Export/reveal/purge, backup/restore, key/credential runbooks | P4M and minimal-audit proof |
| QAO-05 | B6 locked demonstration | L | All MVP packages | Seeded 12-member demo, scripted scenarios, support/runbooks | Signed evidence; alpha veto clear |

# 5. Delivery increments and critical path

Figure 2. Security and QA begin early and continue; they are not a final cleanup phase.

| Increment | Runnable outcome | Exit condition |
| --- | --- | --- |
| I0 — controlled skeleton | Monorepo builds; Compose/staging has locked network; contracts generate typed clients. | FND-01…06 green; no secret or carrier path. |
| I1 — thin simulator call | One seeded member enrolls, receives grant, places simulated answered call, sees debit/history. | Single correlation trace; authoritative answer; one lease; no negative time. |
| I2 — multi-member product | 12 configurable members, requests/fairness, queue, contacts, admin member/grant operations. | Race, permission, allocation, queue and offline cases pass. |
| I3 — full call semantics | Caps, 10-second reconnect, DTMF, late events, finalizing/reconciliation, retention. | State/property/fault suites show no orphan/duplicate/underflow. |
| I4 — locked real-adapter parity | Real driver and home edge run fake/vendor scenarios with activation/kill enforcement. | Shared conformance and no-carrier-command proof. |
| I5 — hardened clients/operations | Admin config/audit/incidents; Android a11y/localization/security; monitoring/runbooks. | Security/privacy/device/backup/restore evidence. |
| I6 — B6 demonstration | Production-shaped locked deployment and scripted 12-member acceptance. | Alpha signs evidence; all veto conditions clear. |

## 5.1 Critical path

FND-01 → FND-03 → BE-01/BE-06/BE-07 → TEL-02, then TEL-03 and TEL-04/TEL-05 in parallel → AND-04/AND-05 → TEL-06/TEL-07/TEL-08 → QAO-02/QAO-03 → QAO-05. Adding agents outside this path improves breadth; adding agents to the same serialized contract does not.

## 5.2 Earliest useful demonstrations

- Contract demo: generated Android/admin clients consume one authoritative error/state catalogue.

- Safety demo: every locked layer independently rejects a real originate envelope.

- Simulator demo: controlled busy/no-answer/answer/reconnect/cap/finalization scenarios with synchronized UI and ledger.

- Privacy demo: masked admin list, step-up reveal, audit fact, P4M purge, and no recording endpoint.

- Operations demo: line uncertainty enters quarantine; restart/reconciliation prevents reuse until proven idle.

# 6. Agent operating model

| Role | Model policy | Owns | May not do |
| --- | --- | --- | --- |
| Primary integration lead | Codex root | Plan, task briefs, contract change queue, integration, user decisions. | Silently broaden scope or waive evidence. |
| Alpha overseer | GPT-5.6 Sol | Semantic/security review, cross-workstream consistency, veto and gate sign-off. | Act as a volume coding worker or approve own implementation. |
| Critical implementation agent | Separate GPT-5.6 Sol | State, ledgers, leases, auth/recovery, encryption, migrations, PBX concurrency, activation/kill. | Independently approve its own critical work. |
| Backend/data agent | GPT-5.6 Terra for contract-bounded handlers/jobs | Non-critical BE packages within accepted contracts. | Change adapter/call/identity contracts unilaterally. |
| Media/adapter agent | GPT-5.6 Terra for fixtures/integration; Sol for critical control | TEL packages and telephony fixtures. | Use live credentials/routes or weaken lock for testing. |
| Android agent | GPT-5.6 Terra | AND packages, device tests, UX semantics. | Treat local state/timer/device ID as authority. |
| Admin agent | GPT-5.6 Terra | WEB packages and browser tests. | Expose activation toggle or unrestricted sensitive data. |
| QA/security/ops agent | Terra for harnesses; Sol for threat/veto review | QAO packages, evidence automation, runbooks. | Mark an owner team's untested assertion as evidence. |

## 6.1 Concurrency policy

- Maximum active work is limited to one integration task plus three bounded agent tasks; unused slots are preferable to conflicting edits, and alpha remains available at critical checkpoints.

- A wave starts only when each package has immutable preconditions and disjoint path ownership.

- Contracts, migrations touching shared tables, call reducer, identity lifecycle, and activation controls have a single writer at a time.

- Review agents inspect commits/evidence and do not simultaneously author the same package.

- When an agent finds missing authority or a contract defect, it stops and files a change record; it does not improvise a local exception.

- TEL-01, TEL-03, TEL-07, TEL-08, BE-06, BE-07, and critical AND-05 media/control work use a separate Sol implementation agent or require direct alpha review; alpha never signs work it materially authored.

## 6.2 Standard agent brief

| Brief field | Required content |
| --- | --- |
| Objective | One externally verifiable outcome, not a broad role. |
| Inputs | Exact PRD/design/ADR/contract versions and existing fixtures. |
| Allowed paths | Explicit directories/files; shared paths read-only unless granted. |
| Must preserve | Named invariants, privacy classes, activation locks, compatibility. |
| Deliverables | Code, migrations, generated artifacts, tests, telemetry, docs/runbook. |
| Acceptance | Exact commands/scenarios and evidence files. |
| Failure protocol | Stop conditions, change-record path, no guess/waiver behavior. |
| Handoff | Commit, changed-contract summary, residual risks, reproducible test output. |

## 6.3 Review cadence

- Agent self-check: focused tests, static checks, diff review, contract/evidence inventory.

- Peer/domain check: consumer compatibility, migration, observability, rollback, failure semantics.

- QA/security check: negative cases, privacy scan, idempotency/race/fault evidence.

- Alpha check for semantic/security-critical changes: invariant trace, adversarial scenarios, veto decision.

- Integration lead merges, runs required aggregate suites, and updates the evidence ledger.

## 6.4 Branch and evidence discipline

- Protected main; temporary integration/B1…B6 branches; isolated agent/<work-package-id> branches or worktrees.

- Critical changes require two independent approvals: alpha plus the consumer or verification lane.

- No agent merges its own safety-critical work; root performs the integration merge after approvals.

- Gate evidence lives at evidence/<gate>/<commit>/ with baseline hashes, tool versions, seeds, raw reports, artifact hashes, reviewers, exceptions, and residual risks.

- Feature-development lock remains active until B2 semantic contracts and golden vectors are approved.

# 7. Verification strategy

## 7.1 Test layers

| Layer | Primary subjects | Required examples | Cadence |
| --- | --- | --- | --- |
| Pure unit/property | Parsers, reducers, fairness, ledgers, time, config. | Unicode +291, underflow, duplicate orderings, month-end, cap boundary. | Every change |
| Contract/conformance | OpenAPI/events/adapter/PBX normalization. | Golden fixtures, backward compatibility, simulator and real parity. | Every change |
| Database integration | Transactions, locks, epochs, outbox/inbox, purge. | Concurrent calls, crash-after-commit, stale event, restore then purge. | Every change |
| Media integration | Asterisk, TURN, WebRTC, app leg, cap/watchdog. | Early media, answer truth, DTMF redaction, reconnect, network loss. | Daily/affected change |
| Client UI | Compose/admin semantics, offline, roles, localization/a11y. | No false Connected, demo banner, reveal confirmation, RTL +291. | Every change + device nightly |
| End-to-end | Full seeded stack. | Enroll/grant/call/history, queue claim, finalization, config rollback. | Daily/release |
| Fault/chaos | DB/PBX/worker/tunnel/KMS/gateway/monitoring/deploy. | No duplicate/orphan/free-uncertain line; admission stops safely. | Nightly/release |
| Security/privacy | Identity, authz, toll fraud, logs, secrets, recording. | Replay/injection/stale generation/reveal/no-server-recording. | Every critical change/release |

## 7.2 Semantic invariant suite

- Available seconds is a non-negative integer; shortfall is a distinct type and cannot authorize a call.

- At most one active or uncertain line owner exists initially; timeout never frees uncertain ownership.

- Only authoritative remote answer starts connected seconds; early media/app connection never does.

- Every transition is legal/monotonic or becomes a duplicate/stale/reconciliation result; terminal facts are immutable.

- Admission reservation and ledger mutation are atomic; duplicate requests/events cannot duplicate debit, grant, call, or release.

- Every carrier command has current activation generation, line/lease epoch, route policy, sequence, deadline, and idempotency key.

- No plaintext destination, DTMF, OTP, token, SIP credential, or media appears in logs, analytics, URLs, push, or crash output.

- Admin/server has no API, storage object, diagnostic path, or backup containing a member recording.

## 7.3 Locked-route negative proof

- Enumerate every originate entry point: API, worker, PBX dial plan, adapter command, edge transport, management protocol.

- Run a generated matrix over missing/stale/mismatched evidence, generation, route, epoch, identity, policy, monitoring, KMS, and network capability.

- Assert rejection occurs independently at each layer and that no fake transport records an outbound carrier command.

- Attempt ordinary admin/config/API manipulation, stale replay, direct PBX route, direct adapter call, and network bypass.

- Archive sanitized command/event traces, network-policy results, config hashes, test seed, build provenance, and alpha verdict.

## 7.4 Device and browser matrix

- Collect all 12 Android models, OS versions, vendors, audio/Bluetooth devices, battery restrictions, and primary networks before minimum-SDK freeze.

- Run enrollment/recovery, foreground/background/lock screen, speaker/wired/Bluetooth, Wi-Fi↔mobile, 9-second reconnect, 10-second termination, and process-kill scenarios.

- Admin browser coverage includes current Chrome/Edge/Safari responsive widths, keyboard-only, screen reader basics, session expiry, and step-up recovery.

- Tigrinya sample/pseudo-localization and Arabic RTL prototype preserve +291/DTMF LTR order and do not clip dynamic text.

# 8. Security, privacy, and operations implementation

## 8.1 Security workstream

| Milestone | Required output | Gate |
| --- | --- | --- |
| Threat model baseline | Assets, trust boundaries, attacker stories, abuse cases, control mapping. | Before thin vertical slice |
| Identity review | Invite/OTP/Keystore/session/migration/recovery adversarial tests. | Before multi-member demo |
| Telephony review | Toll fraud, route injection, caller ID, replay, gateway/PBX exposure, orphan leg. | Before real-adapter merge |
| Privacy review | Data map, number encryption/reveal, telemetry, retention, backup, local recording boundary. | Before B4 closure |
| Release review | SAST/dependencies/secrets/SBOM/provenance, penetration test, residual risk. | Before B6 |

## 8.2 Environments

| Environment | Adapters/routes | Data | Purpose |
| --- | --- | --- | --- |
| Local | Simulator + real fake transport; no gateway network. | Synthetic only. | Fast development and deterministic tests. |
| CI | Ephemeral simulator/fake vendor/PBX; deny egress by policy. | Seeded fixtures. | Merge and fault evidence. |
| Staging | Simulator selected; real driver DRY_RUN/locked; no carrier credentials. | Synthetic named demo users. | Production-shaped integration and B6 rehearsal. |
| Locked production candidate | Same images; activation material absent; PBX route disabled; network denied. | Approved 12-member onboarding only after privacy readiness. | Deployability/operations evidence, not live calls. |

## 8.3 Operational readiness

- Runbooks: deploy/drain/rollback, incident severity, line quarantine/reconciliation, gateway task, key/credential rotation, backup/restore, retention purge, privacy request, and kill modes.

- Alerts: API/DB/PBX/TURN/tunnel/gateway/SIM, stale/uncertain line, cap/watchdog, activation attempt/change, monitoring loss, ledger mismatch, backup/purge/reveal anomalies.

- Dashboards use non-sensitive labels and one correlation ID across app, API, worker, PBX, adapter, ledgers, reconciliation, and audit.

- A simulated monthly restoration proves encrypted backup integrity and reruns retention after restore.

- Critical live-route monitoring loss is implemented even while locked and tested to stop admission after the configured bound.

## 8.4 Deployment safety

- Build immutable signed images and SBOM; verify provenance before promotion.

- Run migration expand phase, compatibility tests, and backup checkpoint.

- Stop new calls or drain according to change class; never interrupt by ordinary deploy accident.

- Deploy control/API/worker, then media/edge, then clients under compatible contracts.

- Verify health, config acknowledgements, route lock, activation generation absence, and synthetic simulator canary.

- Complete contract phase only after rollback window and consumer evidence; rollback publishes new config/migration action rather than erasing history.

# 9. Build gates, evidence, and veto authority

| Gate | Mandatory evidence | Approver |
| --- | --- | --- |
| B1 requirements | PRD v0.3, Product Design v0.2, CAR-01…08, decisions and terminology frozen; no unresolved build blocker. | Owner + primary + alpha |
| B2 semantic/domain | State/ledger/config/error/fairness models and property-test catalogue independently reviewed. | Alpha |
| B3 architecture/contract | Media/lease/adapter/network/privacy spikes; standard SIP line + telemetry plugin surface; ADR-010/011/014; locked topology and rollback proven. | Primary + alpha |
| B4 security/privacy | Threat/control matrix, identity/telephony/privacy tests, no critical/high exploitable finding. | Security reviewer + alpha |
| B5 locked integration | Simulator and real fake-transport conformance, client E2E, faults, kill modes, retention/restore. | QA + primary + alpha |
| B6 locked demonstration | Signed artifacts/SBOM, 12-member scripted demo, operations/evidence pack, 100% traceability, persistent demo labeling, packet/egress no-carrier proof. | Owner + alpha |

## 9.1 Package definition of done

- Named requirement/invariant and accepted contract are linked.

- Code, migration, generated artifacts, feature/activation posture, tests, telemetry, documentation, and rollback are complete.

- Happy, boundary, negative, duplicate, stale, permission, failure, and recovery cases pass at the package's required layers.

- No disallowed secret/PII/logging path exists; dependencies are pinned/scanned and licenses recorded.

- Evidence is reproducible from a clean checkout and indexed by commit/build/config/test seed.

- Owner/reviewer approvals are attributable; residual risk and follow-up are explicit, never hidden in comments.

## 9.2 Build-start veto conditions

- PRD v0.3, Product Design v0.2, or the invariant catalogue are inconsistent, or the plan assigns two writers to a serialized authority.

- Contract change protocol, test/evidence storage, branch protection, secrets policy, or locked network baseline is missing.

- Any planned task requires live SIM credentials, carrier route, ordinary activation UI, or unapproved hardware interoperability.

- The real adapter package is a placeholder rather than production-intent code plus shared conformance requirements.

- No owner exists for call reducer, ledgers, identity/device lifecycle, activation controls, privacy schema, or release evidence.

- An agent brief permits semantic improvisation, cross-package edits, or marking unverified behavior complete.

- The planned build can represent negative callable time, floating-point time/money, impossible transition, unfenced line, blind originate retry, or unrestricted route.

- No alpha review capacity exists for critical contract/security changes.

## 9.3 Merge/release veto conditions

- A required test/evidence artifact is absent, flaky without quarantine/root cause, or not reproducible.

- Any locked configuration can emit a carrier command, any stale generation/epoch is accepted, or an uncertain line can be freed by timeout.

- UI truth diverges from authoritative state, including demo, answer, duration, balance, outage, finalization, kill, or verification status.

- PII/DTMF/credentials/media leak to telemetry; reveal lacks reason/step-up; recording is server-accessible or consentless.

- Critical/high exploitable security issue, migration/rollback uncertainty, failed restore, or unavailable monitoring/kill control remains.

# 10. Effort, schedule policy, and risks

## 10.1 Planning range

| Milestone | Likely elapsed range | Dominant uncertainty |
| --- | --- | --- |
| I0 controlled skeleton | 1–2 weeks | Toolchain, contract generation, deployment account choices. |
| I1 thin simulator call | 3–5 additional weeks | Android WebRTC/Asterisk audio and authoritative event mapping. |
| I2–I3 complete simulator MVP | 5–8 additional weeks | Device diversity, race/fault semantics, admin breadth. |
| I4 locked real-adapter parity | 3–6 additional weeks | SIP gateway compliance and optional vendor telemetry fixture quality. |
| I5–I6 hardening and B6 | 3–5 additional weeks | Fault/security remediation, 12-device QA, evidence closure. |
| Overall B6 candidate | 15–24 elapsed weeks with disciplined parallel waves | Spikes and validation dominate; more agents cannot remove serialized risk. |

The first thin end-to-end result arrives far earlier than B6. Calendar estimates are recalculated after TEL-01 and the exact vendor-protocol investigation; they must not be converted into fixed promises before those spikes close.

## 10.2 Risk register

| Risk | Early signal | Containment / decision |
| --- | --- | --- |
| Android WebRTC/audio instability | TEL-01 fails routes/background/reconnect on target devices. | Spike first; choose maintained library or narrow OS matrix with owner decision. |
| Vendor adapter protocol mismatch | No credible emulator/API/CDR/remote-hangup semantics. | Keep driver transport isolated; require vendor evidence; exact hardware moves to L1. |
| Carrier activation misunderstanding | Implementation status interpreted as authorization. | Separate lifecycle labels and persistent demo banner; no ordinary Enable. |
| Semantic drift under parallelism | Duplicate enums/parsers/ledger calculations appear. | Generated contracts, one writer, change records, alpha review. |
| Privacy leakage in telemetry | Destination/DTMF appears in fixture or log scan. | Redaction at source, canary secrets/PII, fail CI, rotate affected material. |
| One-line uncertainty/orphan call | Timeout/restart marks line free without evidence. | Quarantine, PBX/local caps, query not retry, reconciliation gate. |
| Device diversity | Vendor battery/audio behavior breaks foreground call. | Collect 12-device matrix early; automated/manual device evidence. |
| Cloud/home outage | New call or kill path depends on one unavailable component. | Fail admission; PBX/local bounded termination; truthful status and physical runbook. |
| Scope/config explosion | Every request becomes a new setting or branch. | Typed catalogue, immutable constraints, owner/change approval, defer non-MVP. |

## 10.3 Decision checkpoints

- After TEL-01: confirm Android WebRTC packaging, minimum OS, audio integration, and Asterisk event approach.

- After vendor-protocol investigation: confirm fake transport, exact adapter boundaries, and whether locked real-driver completion is feasible without hardware.

- After I1: validate user/admin semantic comprehension before multiplying screens.

- After B4: decide whether recording skeleton remains compiled-out or feature-gated disabled.

- Before B6: confirm staging cloud/provider, monthly budget, device matrix, support operator, and acceptance participants.

# 11. Initial execution queue

First implementation wave Start only FND-01, FND-02, FND-05 discovery, and TEL-01 test-harness preparation. Do not begin feature UI, database domain implementation, PBX routing, or real-driver transport until the semantic catalogue and contract ownership are approved.

| Order | Task | Owner | Precondition | Exit evidence |
| --- | --- | --- | --- | --- |
| 1 | Approve this plan and alpha memo; freeze B1/B2 source versions. | Owner / primary / alpha | PRD v0.3 + design v0.2 | Signed build-start decision |
| 2 | Create repository skeleton, ownership, decision/evidence templates. | Platform agent | Plan approved | Clean reproducible bootstrap |
| 3 | Publish semantic catalogue and ADR shells. | Primary / contract agent; alpha reviews | Repository skeleton | B2 review record |
| 4 | Publish v1 API/event/adapter schemas and generators. | Contract agent | Semantic catalogue | Compatibility/golden-fixture suite |
| 5 | Create locked local/CI topology and egress-deny proof. | Platform agent | Repository + contract envelope | No carrier-reachable path |
| 6 | Run Android–Asterisk spike against simulator only. | Media + Android agents | Locked topology | TEL-01 decision evidence |
| 7 | Plan I1 thin vertical slice from spike outcome. | Primary + alpha | B3 spike/contract evidence | Bounded package briefs |

## 11.1 Owner decisions needed before code wave

- Approve the implementation plan and alpha veto model.

- Authorize creation of the source repository and CI environment; select Git hosting if not already available.

- Provide the 12-device inventory when requested during TEL-01/AND planning.

- Select a provisional monthly cloud-spend ceiling before staging; provider choice may wait for regional measurements.

- Confirm whether Tigrinya strings are translated during I5 or only the localization-ready sample ships at B6.

# 12. Traceability index

| Requirement area | Primary packages | Gate evidence |
| --- | --- | --- |
| IAM-01…09 | BE-02, AND-02, WEB-01/03, QAO-02 | B2, B4, B5 |
| MIN-01…09 | BE-05, AND-06, WEB-02, QAO-01/03 | B2, B5 |
| CALL-01…11 | BE-01/06/07, TEL-01…05, AND-03…05 | B2, B3, B5 |
| QUE-01…06 | BE-08, AND-06, QAO-03 | B5 |
| DATA-01…09 | BE-04/09, AND-03/06, WEB-04, QAO-04 | B4, B5 |
| REC-01…07 | AND-07, QAO-02/04 | B4, B5 |
| ADM-01…08 | WEB-01…06, BE-02/03/04, TEL-07 | B4, B5 |
| CAR-01…08 | TEL-04…08, BE-03/07, WEB-05, QAO-02/03/05 | B3, B4, B5, B6 |
| L10N/A11Y | AND-01/08, WEB-01, QAO-05 | B5, B6 |
| NFR/security/operations | FND-04…06, QAO-01…05 | B3…B6 |

## 12.1 Authoritative planning artifacts

- PRD v0.3: product scope, behavior, semantics, non-functional requirements, CAR-01…08, build/live gates.

- Product Design v0.2: architecture, trust boundaries, selected standards-based real integration surface, Android/admin UX, security, operations, alpha vetoes.

- Implementation Plan v0.1: work packages, sequencing, ownership, evidence, agent protocol, build-start veto.

- Future repository artifacts: ADRs, threat model, API/event/adapter schemas, test/evidence ledger, runbooks, release records.

# 13. Technical references

| Ref | Source | Link |
| --- | --- | --- |
| R1 | Asterisk, Configuring Asterisk for WebRTC Clients | Open source |
| R2 | Ktor, WebSockets in Ktor Server | Open source |
| R3 | WebRTC project overview | Open source |